## Backend Phases
IND64 Backend: Delivery Phases
Phase | Name | Backend Scope | Blocked By / Dependencies | Status
1 | Foundation | PostgreSQL schema and migrations; sessions; OTP login; CSRF; role and ownership authorization | None | In progress
2 | Catalog and Onboarding | Seed data; artist applications and moderation; packages; media uploads; shortlist | Artist approval and identity check decisions | Not started
3 | Booking and Scheduling | Booking requests; quotes; reservations; cancellation rules; dashboard summaries | Booking duration, travel/setup buffers, and team capacity decisions | Not started
4 | Conversations and Notifications | Participant-scoped messages; read markers; outbox and worker; SMS and email jobs | SMS and email provider choice | Not started
5 | Money | Payment orders; signed webhooks; ledger; refunds; payouts; reconciliation | Payment provider; commission, deposit, and cancellation policy | Not started
6 | Launch Readiness | Restore drills; monitoring; reconciliation checks; policy confirmation (backend-only, no UI) | Hosting decisions; business policies from Phase 5 | Not started

## Summary
Remaining phases
Completed phases
Total phases